## Mudit Prashar
To-do list
To be completed by: |  | 2019-11-17 |  | Name Mudit Prashar
Deadline: |  | 2019-11-18
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Alter SalesManagers, DimOrderDate, DimOccupation Table | 2019-11-05 | 2019-11-09 |  | 4
100% | Replace Identity Key to Sequence (SalesManagers, DimOrderDate, DimOccupation Table) | 2019-11-09 | 2019-11-14 |  | 5
100% | IMPORTANT: Create Stored Procedure (Get rid of foreign keys, Add all foreign keys, Truncate all individual table data) | 2019-11-09 | 2019-11-15 |  | 6
100% | Create Stored Procedures (Product, ProductCategory, ProductSubcategory) | 2019-11-09 | 2019-11-16 |  | 7
100% | Tracking Documents & Project Planner | 2019-11-05 | 2019-11-17 |  | 12
100% | Final Project File Organization + Submission | 2019-11-18 | 2019-11-18 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Dylan Rambarran
To-do list
To be completed by: |  | 2019-11-17 |  | Name Dylan Rambarran
Deadline: |  | 2019-11-18
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Alter DimCustomer, DimProduct, DimTerritory Table | 2019-11-05 | 2019-11-09 |  | 4
100% | Replace Identity Key to Sequence Object (DimCustomer, DimProduct, DimTerritory Table) | 2019-11-09 | 2019-11-14 |  | 5
100% | Create Stored Procedures (DimTerritory, SalesManager,OrderDate, Occupation) | 2019-11-09 | 2019-11-16 |  | 7
100% | Create Stored Procedure (Fact) | 2019-11-15 | 2019-11-16 |  | 1
100% | Powerpoint And Video | 2019-11-16 | 2019-11-17 |  | 1
100% | Final Project File Organization + Submission | 2019-11-18 | 2019-11-18 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Thomas Jimenez
To-do list
To be completed by: |  | 2019-11-17 |  | Name Thomas Jimenez
Deadline: |  | 2019-11-18
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Add DbSecurity.UserAuthorization & Add Process.WorkflowSteps, DimProductCategory, DimProduct Table | 2019-11-05 | 2019-11-13 |  | 8
100% | Replace Identity Key to Sequence (Fact, DimMaritalStatus, DimGender Table) | 2019-11-09 | 2019-11-14 |  | 5
100% | Create Stored Procedures for (DimGender,DimCustomer,DimMaritalStatus) | 2019-11-09 | 2019-11-16 |  | 7
100% | Create Stored Procedure (Workflow) | 2019-11-15 | 2019-11-17 |  | 2
100% | Overseeing the Project Progress | 2019-11-05 | 2019-11-18 |  | 13
100% | Final Project File Organization + Submission | 2019-11-18 | 2019-11-18 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")