## Mudit Prashar
To-do list
To be completed by: |  | 2019-10-19 |  | Name Mudit Prashar
Deadline: |  | 2019-10-22 |  | Date 9/26/19
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Start and Continously Update Long Term Project Tracker | 2019-09-26 | 2019-10-19 |  | 23
100% | Plan + Implement 4 Simple Queries and 1 Complex | 2019-09-26 | 2019-09-27 |  | 1
100% | Plan + Implement 1 Simple and 5 Medium Queries | 2019-09-27 | 2019-10-04 |  | 7
100% | Plan+ Implement 3 Medium and 2 Complex Queries | 2019-10-05 | 2019-10-08 |  | 3
100% | Plan+ Implement 4 Complex Queries | 2019-10-08 | 2019-10-11 |  | 3
100% | Word Template Document + Final SQL File Submission | 2019-10-11 | 2019-10-18 |  | 7
100% | Individual Powerpoint Work - 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + List of all queries | 2019-10-12 | 2019-10-19 |  | 7
100% | Group Powerpoint Work - Group's 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + Assist with any final edits | 2019-10-18 | 2019-10-19 |  | 1
100% | Participate in Voice Annotated Powerpoint Presentation + Voice Annotated JDBC Execution of Groups Top Queries | 2019-10-18 | 2019-10-19 |  | 1
100% | Final Project File Organization + Submission | 2019-10-19 | 2019-10-19 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Jianguo Jin
To-do list
To be completed by: |  | 2019-10-19 |  | Name Jianguo Jin
Deadline: |  | 2019-10-22 |  | Date 9/26/19
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Plan + Implement 4 Simple Queries and 1 Complex | 2019-09-26 | 2019-09-27 |  | 1
100% | Plan + Implement 1 Simple and 5 Medium Queries | 2019-09-27 | 2019-10-04 |  | 7
100% | Plan+ Implement 3 Medium and 2 Complex Queries | 2019-10-05 | 2019-10-08 |  | 3
100% | Plan+ Implement 4 Complex Queries | 2019-10-08 | 2019-10-11 |  | 3
100% | Word Template Document + Final SQL File Submission | 2019-10-11 | 2019-10-18 |  | 7
100% | Individual Powerpoint Work - 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + List of all queries | 2019-10-12 | 2019-10-19 |  | 7
100% | Group Powerpoint Work - Group's 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + Assist with any final edits | 2019-10-18 | 2019-10-19 |  | 1
100% | Add Additional Required Slides for Group Presentation | 2019-10-18 | 2019-10-19 |  | 1
100% | Participate in Voice Annotated Powerpoint Presentation + Voice Annotated JDBC Execution of Groups Top Queries | 2019-10-18 | 2019-10-19 |  | 1
100% | Final Project File Organization + Submission | 2019-10-19 | 2019-10-19 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Thomas Jimenez
To-do list
To be completed by: |  | 2019-10-19 |  | Name Thomas Jimenez
Deadline: |  | 2019-10-22 |  | Date 9/26/19
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Plan + Implement 5 Simple Queries | 2019-09-27 | 2019-10-02 | 2019-10-05 | 5 | Joined group later because original group disbanded
100% | Plan + Implement 5 Medium Queries | 2019-10-02 | 2019-10-05 |  | 3
100% | Plan + Implement 3 Medium and 2 Complex Queries | 2019-10-05 | 2019-10-08 |  | 3
100% | Plan + Implement 5 Complex Queries | 2019-10-08 | 2019-10-11 |  | 3
100% | Word Template Document + Final SQL File Submission | 2019-10-11 | 2019-10-18 |  | 7
100% | Individual Powerpoint Work - 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + List of all queries | 2019-10-12 | 2019-10-19 |  | 7
100% | Code Java GUI Application with JDBC Execution | 2019-10-16 | 2019-10-18 |  | 2
100% | Group Powerpoint Work - Group's 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + Assist with any final edits | 2019-10-18 | 2019-10-19 |  | 1 |  | `q
100% | Participate and Edit/Submit Voice Annotated Powerpoint Presentation + Voice Annotated JDBC Execution of Groups Top Queries | 2019-10-18 | 2019-10-19 |  | 1
100% | Final Project File Organization + Submission | 2019-10-19 | 2019-10-19 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Serena Burton
To-do list
To be completed by: |  | 2019-10-19 |  | Name Serena Burton
Deadline: |  | 2019-10-22 |  | Date 9/26/19
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Plan + Implement 4 Simple Queries and 1 Complex | 2019-09-26 | 2019-09-27 |  | 1
100% | Plan + Implement 1 Simple and 5 Medium Queries | 2019-09-27 | 2019-10-04 |  | 7
100% | Plan+ Implement 3 Medium and 2 Complex Queries | 2019-10-05 | 2019-10-08 |  | 3
100% | Plan+ Implement 4 Complex Queries | 2019-10-08 | 2019-10-11 |  | 3
100% | Word Template Document + Final SQL File Submission | 2019-10-11 | 2019-10-18 |  | 7
100% | Individual Powerpoint Work - 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + List of all queries | 2019-10-12 | 2019-10-19 |  | 7
100% | Group Powerpoint Work - Group's 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + Assist with any final edits | 2019-10-18 | 2019-10-19 |  | 1
100% | Participate in Voice Annotated Powerpoint Presentation + Voice Annotated JDBC Execution of Groups Top Queries | 2019-10-18 | 2019-10-19 |  | 1 |  | `q
100% | Final Project File Organization + Submission | 2019-10-19 | 2019-10-19 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Jerry Chacha
To-do list
To be completed by: |  | 2019-10-19 |  | Name Jerry Chacha
Deadline: |  | 2019-10-22 |  | Date 9/26/19
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Compile Meeting Notes For Group Meetings | 2019-09-26 | 2019-10-19 |  | 23
100% | Plan + Implement 4 Simple Queries and 1 Complex | 2019-09-26 | 2019-09-27 |  | 1
100% | Plan + Implement 1 Simple and 5 Medium Queries | 2019-09-27 | 2019-10-04 |  | 7
100% | Plan+ Implement 3 Medium and 2 Complex Queries | 2019-10-05 | 2019-10-08 |  | 3
100% | Plan+ Implement 4 Complex Queries | 2019-10-08 | 2019-10-11 |  | 3
100% | Word Template Document + Final SQL File Submission | 2019-10-11 | 2019-10-18 |  | 7
100% | Individual Powerpoint Work - 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + List of all queries | 2019-10-12 | 2019-10-19 |  | 7
100% | Group Powerpoint Work - Group's 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + Assist with any final edits | 2019-10-18 | 2019-10-19 |  | 1 |  | `q
100% | Participate in Voice Annotated Powerpoint Presentation + Voice Annotated JDBC Execution of Groups Top Queries | 2019-10-18 | 2019-10-19 |  | 1
100% | Final Project File Organization + Submission | 2019-10-19 | 2019-10-19 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Steven Marmolejo
To-do list
To be completed by: |  | 2019-10-19 |  | Name Steven Marmolejo
Deadline: |  | 2019-10-22 |  | Date 9/26/19
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Plan + Implement 4 Simple Queries and 1 Complex | 2019-09-26 | 2019-09-27 |  | 1
100% | Plan + Implement 1 Simple and 5 Medium Queries | 2019-09-27 | 2019-10-04 |  | 7
100% | Plan+ Implement 3 Medium and 2 Complex Queries | 2019-10-05 | 2019-10-08 |  | 3
100% | Plan+ Implement 4 Complex Queries | 2019-10-08 | 2019-10-11 |  | 3
100% | Word Template Document + Final SQL File Submission | 2019-10-11 | 2019-10-18 |  | 7
100% | Individual Powerpoint Work - 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + List of all queries | 2019-10-12 | 2019-10-19 |  | 7
100% | Group Powerpoint Work - Group's 3 Best Queries, 3 Worst Queries, 3 Fixed Worst Queries + Assist with any final edits | 2019-10-18 | 2019-10-19 |  | 1
100% | Participate in Voice Annotated Powerpoint Presentation + Voice Annotated JDBC Execution of Groups Top Queries | 2019-10-18 | 2019-10-19 |  | 1 |  | `q
100% | Final Project File Organization + Submission | 2019-10-19 | 2019-10-19 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")