## Mudit Prashar
To-do list
To be completed by: |  | 2019-12-10 |  | Name Mudit Prashar
Deadline: |  | 2019-12-11
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Go Over the Project in Detail | 2019-11-24 | 2019-11-24 |  | 0
100% | Design a new DB on AWS or local AND FIX data Anamolies | 2019-11-26 | 2019-11-30 |  | 4
100% | Create Stored Procedures Including Workflow Procedure | 2019-12-02 | 2019-12-08 |  | 6
100% | Create Queries that support our design | 2019-12-07 | 2019-12-09 |  | 2
100% | Powerpoint + Video | 2019-12-08 | 2019-12-10 |  | 2
100% | Final Project Organization + Submission | 2019-12-11 | 2019-12-11 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Dylan Rambarran
To-do list
To be completed by: |  | 2019-12-10 |  | Name Dylan Rambarran
Deadline: |  | 2019-12-11
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Go Over the Project in Detail | 2019-11-24 | 2019-11-24 |  | 0
100% | Design a new DB on AWS or local AND FIX data Anamolies | 2019-11-26 | 2019-11-30 |  | 4
100% | Create Stored Procedures Including Workflow Procedure | 2019-12-02 | 2019-12-08 |  | 6
100% | Create Queries that support our design | 2019-12-07 | 2019-12-09 |  | 2
100% | Powerpoint + Video | 2019-12-08 | 2019-12-10 |  | 2
100% | Final Project Organization + Submission | 2019-12-11 | 2019-12-11 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")

## Thomas Jimenez
To-do list
To be completed by: |  | 2019-12-10 |  | Name Thomas Jimenez
Deadline: |  | 2019-12-11
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Go Over the Project in Detail | 2019-11-24 | 2019-11-24 |  | 0
100% | Design a new DB on AWS or local AND FIX data Anamolies | 2019-11-26 | 2019-11-30 |  | 4
100% | Create Stored Procedures Including Workflow Procedure | 2019-12-02 | 2019-12-08 |  | 6
100% | Create Queries that support our design | 2019-12-07 | 2019-12-09 |  | 2
100% | Powerpoint + Video | 2019-12-08 | 2019-12-10 |  | 2
100% | Final Project Organization + Submission | 2019-12-11 | 2019-12-11 |  | 0
Formulas:
Number Of Days = DATEDIF([Start By],[Original Due By],"D")